## Summary
Texas River iMessage Canonical User Story Tracker
Generated | 2026-07-02 05:13
Scope | Every frontend-relevant feature currently visible in code
Slash goal operating loop | Create code-backed user stories, test every story, document every error, fix UX/logistics errors, then retest every behavior post-fix
Total stories | 30
Critical stories | 19
Stories not run | 0
Open errors | 0
Stop condition | Continue until remaining improvements are objectively low-value or blocked by product/platform decisions
Phase | Definition of done | Status | Evidence | Next action
1. Inventory | Every code-backed feature has a user story and expected behavior | Complete in this workbook | Feature Stories sheet | Keep tracker updated as code changes
2. Test loop | Every story receives manual or automated result plus evidence | In progress | Test Loop sheet | Continue manual iPhone 16 gameplay across remaining untested stories
3. Fix loop | Every UX/logistics error has source fix and status | Not started | Errors sheet | Patch app in priority order
4. Retest loop | Every fixed story is retested and marked pass/fail | Not started | Feature Stories/Test Loop | Repeat until only low-value or blocked work remains

## Feature Stories
Story ID | Area | Feature | User story | Expected behavior from code | Entry points / IDs | Source files | Current coverage evidence | Feature status | Test status | Errors / UX notes | Priority | Next action
HM-001 | Profile | First-run profile setup | As a new player, I configure my handle and avatar before seeing any join/start action. | If no saved profile exists, the app renders a compact ProfileSetupView with one title, avatar picker, labelled handle field, and bottom save action. Save is disabled until the trimmed handle is non-empty. Saving normalizes name/avatar and moves to lobby/start flow. | profile.name, profile.save, profile.avatar.N | River.swift; GameTableScreen.swift; ProfileSetupView.swift; ProfileStore.swift; ProfileText.swift | ProfileStoreTests; FrontendInteractionContractTests | In progress | Pass | Passed: ProfileSetupView simplified into a compact one-title setup step with no instructional subtitle/helper copy; profile handle now visibly caps at ProfileText.maxNameLength during entry; build-ios-apps test_sim first-run profile setup, whitespace-only rejection, selected avatar accessibility, max-length entry, save gate, and persistence passed on Poker iPhone 16; Swift package suite 306/306. | Critical | Retain exploratory first-run visual pass; whitespace-only rejection, empty save gate, max length, avatar tap, save, and persistence are covered on Poker iPhone 16
HM-002 | Profile | Edit saved profile before joining | As a returning player, I can edit my locally saved profile before taking a lobby or in-progress-game seat. | Lobby/Join prompts show the saved profile summary with a compact pencil edit action. Edit opens profile setup with Cancel only when a saved profile exists. Cancel preserves the prior profile and returns to the active prompt. Once joined, the lobby shows ready/leave actions instead of profile edit controls. | lobby.profileSummary, lobby.editProfile, conversation.profileSummary, conversation.editProfile, profile.cancel | LobbyActions.swift; JoinGameView.swift; MessagesViewControllerRendering.swift; ProfileSetupView.swift | ProfileStoreTests; FrontendInteractionContractTests | In progress | Pass | Passed: build-ios-apps test_sim edit/cancel/save profile flow on Poker iPhone 16 after replacing the text edit affordance with a compact pencil icon target; same suite verifies profile summary/edit controls disappear after joining and ready actions replace them. | High | Retain iMessage multi-participant manual pass; demo verifies saved-profile edit/cancel before joining and no profile edit path after joining
HM-003 | Profile | Local profile persistence | As a player, my handle/avatar should be remembered locally between app launches. | ProfileStore reads/writes the profile locally. Demo app supports -holdemResetProfile for clean UI-test runs. | profile.save | ProfileStore.swift; GameTableScreen.swift | ProfileStoreTests; RiverInteractionTests | Needs regression | Pass | Passed: build-ios-apps test_sim profile save gate, max-length persistence, and relaunch persistence test on Poker iPhone 16. | Critical | Kill/relaunch app and confirm saved identity appears before Join table Retain manual exploratory pass for UX polish.
HM-004 | Conversation | No selected message start prompt | As a configured player in Messages, I can start a new table from an empty conversation state. | With no selected table message and a saved profile, renderer shows StartGameView with saved identity and Start table/Edit profile actions. Start sends a lobby message seeded with the local participant as first seat. | conversation.startTable, conversation.editProfile | MessagesViewControllerRendering.swift; TableMessageRenderer.swift; StartGameView.swift; TableMessageActions.swift | MessageWireHelpers; PayloadSerializationTests | In progress | Pass | Passed: package frontend contract tests for saved-profile start prompt, unified 8pt conversation action button, and TableMessageActions.newLobby. | Critical | Open extension without selected message, start table, inspect new bubble summary Retain manual exploratory pass for UX polish.
HM-005 | Lobby | Join lobby with saved identity | As an invited player, I join the lobby using my saved local profile. | Join lobby operation uses saved name/avatar. Repeated joins are idempotent. Join is disabled when lobby is full. | lobby.join | LobbyView.swift; LobbyActions.swift; LobbyMutation.swift; LobbyMembershipOperation.swift | LobbyTests; TableLobbyOperationTests | In progress | Pass | Passed: build-ios-apps test_sim join table flow on Poker iPhone 16 after simplifying lobby primary buttons to one 8pt rounded shape; lobby operation tests passed in package suite. | Critical | Join as second simulator participant; verify saved handle/avatar and no editable seat name in lobby Retain manual exploratory pass for UX polish.
HM-006 | Lobby | Ready/unready and auto-start | As a seated player, I can ready or unready, and the game starts once at least two seated players are all ready. | Ready button toggles ready state. Lobby.canStart requires at least two seats and all present players ready. Toggle-ready operation carries start seed and turn duration for deterministic hand start. | lobby.ready | Lobby.swift; LobbyReadyOperation.swift; LobbyStart.swift; TableMessageActions.swift; DemoLobby.swift | LobbyTests; TableLobbyOperationTests; InitialHandSetupTests | In progress | Pass | Passed: build-ios-apps test_sim ready-to-start flow on Poker iPhone 16; lobby/start tests passed in package suite. | Critical | Use two players; verify unready prevents start and final ready transitions to table Retain manual exploratory pass for UX polish.
HM-007 | Lobby | Leave lobby | As a seated lobby player, I can leave before the game starts. | Leave lobby removes only the local participant's seat and increments version when the seat existed. After leaving, the pre-join prompt returns with the saved local identity and edit action before rejoin. | lobby.leave | LobbyActions.swift; LobbyMutation.swift; LobbyMembershipOperation.swift; MessagesViewControllerActions.swift | LobbyTests; TableLobbyOperationTests | In progress | Pass | Passed: build-ios-apps test_sim lobby join, leave, saved-identity prompt return, edit affordance return, rejoin, and table observability flow on Poker iPhone 16. | High | Retain iMessage multi-participant manual pass; demo verifies join, leave, saved-identity prompt, edit affordance, and rejoin
HM-008 | Lobby | Demo-only add player | As a local demo tester, I can add stand-in players to start a pass-and-play game. | DemoLobby exposes Add player only when the local demo user is joined and lobby is not full. Real iMessage renderer passes nil so the control is absent. | lobby.addTestPlayer | DemoLobby.swift; LobbyView.swift; LobbyActions.swift; TableMessageRenderer.swift | RiverInteractionTests | In progress | Pass | Passed: build-ios-apps test_sim confirms demo Add player absent before profile and present after join. | Medium | Ensure button absent in Messages flow but present in standalone demo Retain manual exploratory pass for UX polish.
HM-009 | Messages | Compact game bubble opens expanded table | As a seated player viewing a game bubble in compact presentation, I can open the full table. | When seated and not game-over, compact presentation renders CompactSummaryView as a pressable 8pt rounded row with a clear open-table affordance. Open table requests expanded presentation. Expanded renders PokerTableView. | conversation.openTable | TableMessageRenderer.swift; CompactSummaryView.swift; MessagesViewControllerRendering.swift; PokerTableView.swift | FrontendInteractionContractTests | In progress | Pass | Passed: package frontend contract tests for compact seated game rendering, pressable open-table row, and requestExpandedPresentation open action; full RiverInteractionTests suite passed on Poker iPhone 16. | Critical | Tap compact bubble on Poker iPhone 16 and verify expanded table, not stale/join prompt Retain manual exploratory pass for UX polish.
HM-010 | Messages | Invalid payload recovery | As a user opening a corrupted table message, I should see a clear recovery state instead of a broken UI. | Decode failures from selected message render StaleTableView with Invalid table message and invalid-payload context. | conversation.recovery | MessagePayloads.swift; TableMessageRenderer.swift; StaleTableView.swift; MessagesViewControllerRendering.swift | LegacyPayloadTests; PayloadDurabilityTests | In progress | Pass | Passed: package frontend contract tests for invalid selected payload recovery before profile/start fallback. | High | Inject invalid URL payload in unit/UI harness and verify recovery copy Retain manual exploratory pass for UX polish.
HM-011 | Messages | Stale/rejected action recovery | As a player acting on an old bubble, I should be told the table moved on instead of sending bad state. | RevisionStore marks older messages stale. Committer rejects stale/wrong phase/not actor/game-over operations. Renderer shows stale table recovery with reason context. | conversation.recovery | LatestRevisionStore.swift; TableRevisionTracker.swift; TableMessageCommitter.swift; MessagesViewControllerSending.swift; StaleTableView.swift | TableRevisionTests; OperationHistoryTests; InvalidActionTests | In progress | Pass | Passed: package frontend contract tests for stale/rejected action recovery with reason-specific copy. | Critical | Use two bubbles out of order; tap old action and confirm no bad send Retain manual exploratory pass for UX polish.
HM-012 | Messages | Send replacement message | As a player taking any valid action, the app should send an encoded replacement message and dismiss only once Messages accepts the send. | MessageSender creates MSMessage with caption 'River', subcaption summary, summaryText, and encoded URL. Sent means queued for async send; successful send remembers the revision and dismisses. Unchanged dismisses immediately. Send failure expands and shows stale/send-failed context without hiding recovery. | iMessage bubble layout | MessageSender.swift; MessagePayloads.swift; TableMessageCommitter.swift; MessagesViewControllerSending.swift | PayloadSerializationTests; PayloadDurabilityTests | In progress | Pass | Passed: package frontend contract tests for outgoing iMessage bubble caption, subcaption, summaryText, URL, send failure recovery, revision persistence, and dismissal only after send success; build-ios-apps UI test passed on Poker iPhone 16. | Critical | Perform action, verify resulting iMessage bubble summary, success dismissal, and visible recovery on send failure Retain manual exploratory pass for UX polish.
HM-013 | In-progress join | Join next hand from active game | As a player not seated in an active game, I can join the table for the next hand using my saved profile. | Unseated or has-left viewer gets JoinGameView with profile summary/edit and Join next hand. Operation adds player with configured starting stack for the next eligible hand. | conversation.joinGame | TableMessageRenderer.swift; JoinGameView.swift; GameMembershipOperation.swift; NextHandEligibilityTests | JoinGameOperationTests; NextHandEligibilityTests | In progress | Pass | Passed: package frontend contract tests for saved-profile Join next hand prompt, unified 8pt conversation action button, and shared join-game operation tests. | High | Open active game from third participant and join; verify current hand integrity and next-hand inclusion Retain manual exploratory pass for UX polish.
HM-014 | Table | Seat row and board state | As a seated player, I can understand who is seated, whose turn it is, stacks, cards, board, and pot. | PokerTableView composes seats row, BoardView, bottom controls, and hero dock from PokerTablePresentation. BoardView exposes table.board with a deterministic empty/card summary, pot exposes table.pot, and the hero dock shows the saved player name so the active identity is explicit. | table.board, table.pot, table.heroSeat, seat labels | PokerTableView.swift; PokerTableSeatsRow.swift; PlayerSeatView.swift; BoardView.swift; HeroHandDock.swift; HandStrengthBox.swift; PokerTablePresentation.swift | FrontendInteractionContractTests; TableSummaryTests; RiverInteractionTests | In progress | Pass | Passed: build-ios-apps test_sim table observability checks for board, pot, and named hero seat on Poker iPhone 16; frontend contract tests cover table.board label and hero-seat name plumbing. | Critical | Play through preflop/flop/turn/river and check readability at compact iMessage size; keep verifying hero identity remains obvious after each actor/hand transition Retain manual exploratory pass for UX polish.
HM-015 | Table | Current hand display | As the acting player, I can see my identity, hole cards, and hand strength without exposing other players' private cards. | HeroHandDock and HoleCardsView show the current hero's saved player name, hand, and hand strength; reveal/winning card presentation is handled by showdown presentation. Accessibility ID table.holeCards identifies the hero cards. | table.heroSeat, table.holeCards | HeroHandDock.swift; HandStrengthBox.swift; HoleCardsView.swift; PokerTableHeroPresentation.swift; PokerTableShowdownPresentation.swift | FrontendInteractionContractTests; HandResultTests; RiverInteractionTests | In progress | Pass | Passed: build-ios-apps test_sim hole-card and named hero-seat accessibility/readability checks after fixing duplicate table.holeCards elements and anonymous hero dock identity. | Critical | Confirm pass-and-play hero identity changes by actor and other hole cards stay hidden until showdown Retain manual exploratory pass for UX polish.
HM-016 | Table actions | Fold/check/call legal action controls | As the current actor, I only see legal primary actions and can submit them once. | Presentation exposes legalActionsForHero only for current actor. ActionBarView renders fold/check/call based on LegalActions. Core revalidates and rejects illegal actions. | table.action.fold, table.action.check, table.action.call | PokerTableActionArea.swift; ActionBarView.swift; LegalActions.swift; PlayerActionMutation.swift; GameActionApplication.swift | BettingResolutionTests; InvalidActionTests; FullHandMessagePassingTests | In progress | Pass | Passed: build-ios-apps test_sim fold action flow after unifying fold/check/call/raise controls to 8pt rounded action buttons; betting/invalid-action tests passed in package suite. | Critical | Try each street and verify non-actor sees waiting bar, not buttons Retain manual exploratory pass for UX polish.
HM-017 | Table actions | Raise slider and presets | As the current actor, I can choose a valid raise with presets or slider and submit explicitly. | Raise panel clamps selected total to legal min/max. Header shows the selected raise total with close affordance, the slider gets a full-width row, presets include +1 BB, 1/2 pot, pot, and the explicit Raise button submits .raise(to:) then closes. | table.action.raise.expand, table.raise.slider, table.raise.submit, table.raise.preset.1bb, table.raise.preset.halfPot, table.raise.preset.pot, table.raise.close | RaisePanelView.swift; ActionBarView.swift; RaisePreset.swift; LegalActions.swift; RaiseActionMutation.swift | BettingRaiseTests; InvalidActionTests; FrontendInteractionContractTests | Needs regression | Pass | Passed: raise panel simplified into header/full-width slider/preset-submit rows and presets now share the 8pt action-control shape; Swift package suite 306/306 and build-ios-apps test_sim adjusts the slider to min, max, and mid positions, verifies accessible selected values, taps +1 BB, pot, 1/2 pot, close, reopen, and submit through the full RiverInteractionTests suite on Poker iPhone 16. | Critical | Retain exploratory chip/value pass; automated Poker iPhone 16 flow now adjusts the raise slider to min, max, and mid positions, taps +1 BB, pot, 1/2 pot, closes, reopens, and submits
HM-018 | Table actions | Waiting state | As a non-actor or between actions, I see a concise waiting/status row instead of unusable controls. | When no legal hero actions are available and hand is not resolved, PokerTableActionArea renders WaitingBar with presentation.waitingText and table.waiting identifier. Non-actors see the current player's saved name in the waiting copy when available; folded players still get a next-hand message. | table.waiting | PokerTableActionArea.swift; WaitingBar.swift; PokerTableActionPresentation.swift | FrontendInteractionContractTests | In progress | Pass | Passed: package frontend contract tests for non-actor waiting mode, named current-player waiting copy, folded-player waiting copy, table.waiting identifier, and 8pt waiting bar shape. | High | Observe other players' turns and timeout-resolved states; verify named actor waiting copy in multi-participant iMessage Retain manual exploratory pass for UX polish.
HM-019 | Table | Turn clock and timeout | As players take turns, the app should show a shared turn clock and resolve expired turns consistently. | GameState stores turnStartedAt/turnDuration. TurnClock/GameTimeout resolve stale turns lazily when a client loads or acts. Active hero/opponent seat accessibility labels include the normalized turn-clock duration so the timer is not purely visual. | turn clock visual; active seat accessibility labels | TurnClock.swift; GameTimeout.swift; CountdownTimer.swift; DepletingBorder.swift; MessagesViewControllerRendering.swift; HandStrengthBox.swift; PlayerSeatView.swift | TimeoutTests; TimeoutMessagePassingTests | In progress | Pass | Passed: package timeout tests plus frontend contract tests proving render-time timeout resolution, normalized visual clocks, and active seat accessibility labels that include the shared turn-clock duration; full RiverInteractionTests passed on Poker iPhone 16. | High | Wait past timeout on simulator, reopen/act, verify deterministic timeout action Retain manual exploratory pass for UX polish.
HM-020 | Table | Leave active table confirmation | As a seated player, I can leave the active table only after confirming. | PokerTableView overlays LeaveTableButton when not game-over. The leave entry point is a visible 44pt icon control, exposes confirmation state for accessibility, reveals cancel/confirm actions, and confirm sends leaveGame. Core marks player left/forfeits hand as appropriate. | table.leave, table.leave.cancel, table.leave.confirm | PokerTableView.swift; LeaveTableButton.swift; GameLeaving.swift; PlayerLeavingLifecycleTests.swift | LeaveGameOperationTests; PlayerLeavingLifecycleTests | Needs regression | Pass | Passed: visible 44pt leave control with confirmation-state accessibility and unified 8pt framed stay/leave confirmation controls; Swift package suite 306/306 and build-ios-apps leave cancel plus destructive confirm heads-up game-over paths passed on Poker iPhone 16. | High | Retain extended manual multi-player pass to verify excluded players stay out of later hands
HM-021 | Hand lifecycle | Street advancement | As betting completes, the table advances from preflop through flop, turn, river, and showdown. | StreetAdvancement advances only after betting round completion. Board cards are dealt by stage, pot/display summaries update. The standalone UI test now checks board counts at flop, turn, and river, then verifies the showdown/result state and Deal next hand action. | table.board, table.result, table.action.dealNext | StreetAdvancement.swift; GameAdvancement.swift; CardArrayDealing.swift; CommunityCardsView.swift; BoardStatusRow.swift; PokerTableActionArea.swift | StreetAdvancementTests; PartialHandTests; FullHandMessagePassingTests; RiverInteractionTests | In progress | Pass | Passed: package street advancement/full hand tests plus build-ios-apps check/call board-progression UI path on Poker iPhone 16 covering flop, turn, river, showdown result, and Deal next hand. | Critical | Retain iMessage bubble-summary manual pass; standalone Poker iPhone 16 now verifies flop, turn, river, showdown result, and Deal next hand
HM-022 | Hand lifecycle | Uncontested hand result | As players fold, the last active player should immediately win the hand. | UncontestedAward and hand lifecycle assign pot, mark hand complete, and presentation shows a single accessible winner/result banner separate from any Deal next command. | table.result, table.action.dealNext | UncontestedAward.swift; HandLifecycle.swift; PokerTableActionArea.swift; ResultSummaryText.swift | BettingResolutionTests; HandResultTests | In progress | Pass | Passed: build-ios-apps test_sim fold-to-result/deal-next flow after splitting winner status from Deal next command and fixing duplicate table.result accessibility; hand result tests passed. | Critical | Fold all but one player and verify chip movement/result/deal-next Retain manual exploratory pass for UX polish.
HM-023 | Hand lifecycle | Showdown and side pots | As all-in or called hands reach showdown, winnings should be awarded accurately, including split/side pots. | HandEvaluator, ShowdownRanking, SidePotAwarding, and HandSettlement compute ranked winners and payments. UI highlights winning cards and winner text, reveals contesting players' showdown cards, and the seat accessibility summary identifies revealed cards plus winning seats. | table.result, seat labels | HandEvaluator.swift; ShowdownRanking.swift; SidePotAwarding.swift; HandSettlement.swift; PokerTableShowdownPresentation.swift; PlayerSeatView.swift | BestOfSevenTests; SidePotTests; SidePotMessagePassingTests; HandOrderingTests; FrontendInteractionContractTests | In progress | Pass | Passed: package showdown/side-pot/best-of-seven tests plus frontend contract for accessible revealed showdown cards and winning seats; still needs manual all-in UX pass. | Critical | Retain manual all-in/split-pot UX pass; package tests cover side-pot math and frontend contract now covers accessible revealed cards/winners
HM-024 | Hand lifecycle | Deal next hand | As the table finishes a hand, an eligible player can deal the next hand and preserve stacks/seating. | When hand complete and onDealNext exists, action area shows result status and a short Deal next hand command with a stable action identifier. Operation uses new seed, rotates dealer, excludes left/broke players, handles game over, and returns the UI to a fresh hand with an empty board. | table.action.dealNext, table.board | DealNextHandOperation.swift; NextHandLifecycle.swift; NextHandDealer.swift; PokerTableActionArea.swift; BoardView.swift | DealNextHandOperationTests; NextHandDealerTests; NextHandStackTests; GameOverLifecycleTests; RiverInteractionTests | In progress | Pass | Passed: build-ios-apps test_sim deal-next flow with short Deal next hand label, fresh hole cards, cleared board, and hidden deal-next action on Poker iPhone 16; next-hand package tests passed. | Critical | Retain multi-hand manual pass for dealer/stacks; standalone Poker iPhone 16 verifies Deal next hand, fresh hole cards, cleared board, and hidden deal-next action
HM-025 | Game over | Game over presentation | As the final winner or observer, I should see a clear game-over state and no table actions. | If state.isGameOver, renderer shows GameOverView. The finished-game prompt exposes one deterministic accessible element labelled with Game over plus the final summary and announces that no actions are available. In the live table, the result banner distinguishes a final game win from a hand win with 'wins game'. Core rejects further game actions as gameOver. | conversation.gameOver, table.result | GameOverView.swift; TableMessageRenderer.swift; PokerTableActionArea.swift; GameActionApplication.swift; GameOverLifecycleTests.swift | GameOverLifecycleTests; FrontendInteractionContractTests; RiverInteractionTests | In progress | Pass | Passed: package frontend contract tests for game-over renderer ordering, deterministic Game over accessibility label/value, and live table final-result copy that says wins game; game-over lifecycle tests passed; full RiverInteractionTests passed on Poker iPhone 16. | High | Play/eliminate to one winner or construct fixture; verify no leave/action controls and final live table says wins game Retain manual exploratory pass for UX polish.
HM-026 | Text/layout | Stable compact text | As a player using narrow iMessage UI, labels should fit without truncation that hides meaning or shifts layout. | StableText is used on key buttons to constrain one-line text, scale where appropriate, and avoid clunky wrapping in action surfaces. | visible button labels | StableText.swift; ActionControls.swift; LobbyActionButtons.swift; ConversationActionButton.swift; LeaveTableButton.swift; WaitingBar.swift; ProfileSetupView.swift | Not yet run after latest refactor | Needs regression | Pass | Passed: package frontend contract tests after stable-text helper test update, compact open-table affordance polish, tighter first-run profile layout, unified 8pt lobby/conversation/table/leave controls, centralized control radius, and centralized table action/compact control heights in Theme.Metrics; full RiverInteractionTests suite passed on Poker iPhone 16. | Critical | Run full build/test and manually inspect every button in iPhone 16 simulator Retain manual exploratory pass for UX polish.
HM-027 | Accessibility | Automation identifiers | As a tester, every important control should have stable identifiers for UI automation. | HoldemAccessibility centralizes IDs for profile, lobby, conversation, table actions, raise panel, leave confirmation, and waiting/result states. | all HoldemAccessibility IDs | HoldemAccessibility.swift; OptionalAccessibilityIdentifier.swift; UI view files | RiverInteractionTests; FrontendInteractionContractTests | Needs regression | Pass | Passed: build-ios-apps test_sim used key accessibility IDs; frontend contract tests passed, including selected avatar trait, profile preview label, table.board, table.leave accessibility value, conversation.gameOver label/value, and active seat clock labels. | High | Write/expand UI tests to hit every ID in this workbook Retain manual exploratory pass for UX polish.
HM-028 | Rules engine | Payload durability and legacy handling | As the game travels through Messages URLs, state should remain compact, decodable, and backward-compatible. | Payload coders encode table messages/operations through URL-safe payloads. Legacy tests cover prior formats and malformed cases. | MSMessage.url | GamePayloadCoding.swift; GamePayloadURLCoding.swift; GameStateCoding.swift; LobbyCoding.swift; TableOperationPayload.swift; Base64URL.swift | PayloadSerializationTests; PayloadDurabilityTests; LegacyPayloadTests | Needs regression | Pass | Passed: package payload serialization/durability/legacy tests. | Critical | Run package tests after every payload-affecting UI/transport change Retain manual exploratory pass for UX polish.
HM-029 | Rules engine | Duplicate/stale operation protection | As multiple players act through async messages, duplicate or old operations should not corrupt state. | Operation IDs are normalized/history-capped. Applied operation IDs and TableRevisionTracker reject duplicate/stale/wrong-base operations. | operation history | OperationIdentity.swift; TableOperationRecording.swift; TableRevisionTracker.swift; TableMessageOperationPayload.swift | OperationHistoryTests; TableRevisionTests; FullHandMessagePassingTests | Needs regression | Pass | Passed: package operation history/revision tests. | Critical | Replay same operation payload and older revision in tests/manual harness Retain manual exploratory pass for UX polish.
HM-030 | Native app | Standalone pass-and-play demo | As a developer/tester, I can run the standalone app and play a complete local game on one simulator. | River starts GameTableScreen in dark mode. GameController uses local lobby state and pass-and-play current actor as hero. | standalone app flow | River.swift; GameTableScreen.swift; GameController.swift; DemoGameTable.swift | RiverInteractionTests; GameControllerTests | In progress | Pass | Passed: build-ios-apps test_sim standalone pass-and-play smoke path on Poker iPhone 16, including saved-profile identity appearing in the acting hero seat and leave-confirmation game-over copy saying wins game. | High | Reinstall on Poker iPhone 16, play many hands, document UX/logistics issues Retain manual exploratory pass for UX polish.

## Test Loop
Story ID | Scenario | Manual steps | Expected result | Evidence | Result | Error IDs | Fix needed | Retest result
HM-001 | First-run profile setup | Retain exploratory first-run visual pass; whitespace-only rejection, empty save gate, max length, avatar tap, save, and persistence are covered on Poker iPhone 16 | If no saved profile exists, the app renders a compact ProfileSetupView with one title, avatar picker, labelled handle field, and bottom save action. Save is disabled until the trimmed handle is non-empty. Saving normalizes name/avatar and moves to lobby/start flow. | Passed: ProfileSetupView simplified into a compact one-title setup step with no instructional subtitle/helper copy; profile handle now visibly caps at ProfileText.maxNameLength during entry; build-ios-apps test_sim first-run profile setup, whitespace-only rejection, selected avatar accessibility, max-length entry, save gate, and persistence passed on Poker iPhone 16; Swift package suite 306/306. | Pass |  |  | Pass
HM-002 | Edit saved profile before joining | Retain iMessage multi-participant manual pass; demo verifies saved-profile edit/cancel before joining and no profile edit path after joining | Lobby/Join prompts show the saved profile summary with a compact pencil edit action. Edit opens profile setup with Cancel only when a saved profile exists. Cancel preserves the prior profile and returns to the active prompt. Once joined, the lobby shows ready/leave actions instead of profile edit controls. | Passed: build-ios-apps test_sim edit/cancel/save profile flow on Poker iPhone 16 after replacing the text edit affordance with a compact pencil icon target; same suite verifies profile summary/edit controls disappear after joining and ready actions replace them. | Pass |  |  | Pass
HM-003 | Local profile persistence | Kill/relaunch app and confirm saved identity appears before Join table Retain manual exploratory pass for UX polish. | ProfileStore reads/writes the profile locally. Demo app supports -holdemResetProfile for clean UI-test runs. | Passed: build-ios-apps test_sim profile save gate, max-length persistence, and relaunch persistence test on Poker iPhone 16. | Pass |  |  | Pass
HM-004 | No selected message start prompt | Open extension without selected message, start table, inspect new bubble summary Retain manual exploratory pass for UX polish. | With no selected table message and a saved profile, renderer shows StartGameView with saved identity and Start table/Edit profile actions. Start sends a lobby message seeded with the local participant as first seat. | Passed: package frontend contract tests for saved-profile start prompt, unified 8pt conversation action button, and TableMessageActions.newLobby. | Pass |  |  | Pass
HM-005 | Join lobby with saved identity | Join as second simulator participant; verify saved handle/avatar and no editable seat name in lobby Retain manual exploratory pass for UX polish. | Join lobby operation uses saved name/avatar. Repeated joins are idempotent. Join is disabled when lobby is full. | Passed: build-ios-apps test_sim join table flow on Poker iPhone 16 after simplifying lobby primary buttons to one 8pt rounded shape; lobby operation tests passed in package suite. | Pass |  |  | Pass
HM-006 | Ready/unready and auto-start | Use two players; verify unready prevents start and final ready transitions to table Retain manual exploratory pass for UX polish. | Ready button toggles ready state. Lobby.canStart requires at least two seats and all present players ready. Toggle-ready operation carries start seed and turn duration for deterministic hand start. | Passed: build-ios-apps test_sim ready-to-start flow on Poker iPhone 16; lobby/start tests passed in package suite. | Pass |  |  | Pass
HM-007 | Leave lobby | Retain iMessage multi-participant manual pass; demo verifies join, leave, saved-identity prompt, edit affordance, and rejoin | Leave lobby removes only the local participant's seat and increments version when the seat existed. After leaving, the pre-join prompt returns with the saved local identity and edit action before rejoin. | Passed: build-ios-apps test_sim lobby join, leave, saved-identity prompt return, edit affordance return, rejoin, and table observability flow on Poker iPhone 16. | Pass |  |  | Pass
HM-008 | Demo-only add player | Ensure button absent in Messages flow but present in standalone demo Retain manual exploratory pass for UX polish. | DemoLobby exposes Add player only when the local demo user is joined and lobby is not full. Real iMessage renderer passes nil so the control is absent. | Passed: build-ios-apps test_sim confirms demo Add player absent before profile and present after join. | Pass |  |  | Pass
HM-009 | Compact game bubble opens expanded table | Tap compact bubble on Poker iPhone 16 and verify expanded table, not stale/join prompt Retain manual exploratory pass for UX polish. | When seated and not game-over, compact presentation renders CompactSummaryView as a pressable 8pt rounded row with a clear open-table affordance. Open table requests expanded presentation. Expanded renders PokerTableView. | Passed: package frontend contract tests for compact seated game rendering, pressable open-table row, and requestExpandedPresentation open action; full RiverInteractionTests suite passed on Poker iPhone 16. | Pass |  |  | Pass
HM-010 | Invalid payload recovery | Inject invalid URL payload in unit/UI harness and verify recovery copy Retain manual exploratory pass for UX polish. | Decode failures from selected message render StaleTableView with Invalid table message and invalid-payload context. | Passed: package frontend contract tests for invalid selected payload recovery before profile/start fallback. | Pass |  |  | Pass
HM-011 | Stale/rejected action recovery | Use two bubbles out of order; tap old action and confirm no bad send Retain manual exploratory pass for UX polish. | RevisionStore marks older messages stale. Committer rejects stale/wrong phase/not actor/game-over operations. Renderer shows stale table recovery with reason context. | Passed: package frontend contract tests for stale/rejected action recovery with reason-specific copy. | Pass |  |  | Pass
HM-012 | Send replacement message | Perform action, verify resulting iMessage bubble summary, success dismissal, and visible recovery on send failure Retain manual exploratory pass for UX polish. | MessageSender creates MSMessage with caption 'River', subcaption summary, summaryText, and encoded URL. Sent means queued for async send; successful send remembers the revision and dismisses. Unchanged dismisses immediately. Send failure expands and shows stale/send-failed context without hiding recovery. | Passed: package frontend contract tests for outgoing iMessage bubble caption, subcaption, summaryText, URL, send failure recovery, revision persistence, and dismissal only after send success; build-ios-apps UI test passed on Poker iPhone 16. | Pass |  |  | Pass
HM-013 | Join next hand from active game | Open active game from third participant and join; verify current hand integrity and next-hand inclusion Retain manual exploratory pass for UX polish. | Unseated or has-left viewer gets JoinGameView with profile summary/edit and Join next hand. Operation adds player with configured starting stack for the next eligible hand. | Passed: package frontend contract tests for saved-profile Join next hand prompt, unified 8pt conversation action button, and shared join-game operation tests. | Pass |  |  | Pass
HM-014 | Seat row and board state | Play through preflop/flop/turn/river and check readability at compact iMessage size; keep verifying hero identity remains obvious after each actor/hand transition Retain manual exploratory pass for UX polish. | PokerTableView composes seats row, BoardView, bottom controls, and hero dock from PokerTablePresentation. BoardView exposes table.board with a deterministic empty/card summary, pot exposes table.pot, and the hero dock shows the saved player name so the active identity is explicit. | Passed: build-ios-apps test_sim table observability checks for board, pot, and named hero seat on Poker iPhone 16; frontend contract tests cover table.board label and hero-seat name plumbing. | Pass |  |  | Pass
HM-015 | Current hand display | Confirm pass-and-play hero identity changes by actor and other hole cards stay hidden until showdown Retain manual exploratory pass for UX polish. | HeroHandDock and HoleCardsView show the current hero's saved player name, hand, and hand strength; reveal/winning card presentation is handled by showdown presentation. Accessibility ID table.holeCards identifies the hero cards. | Passed: build-ios-apps test_sim hole-card and named hero-seat accessibility/readability checks after fixing duplicate table.holeCards elements and anonymous hero dock identity. | Pass |  |  | Pass
HM-016 | Fold/check/call legal action controls | Try each street and verify non-actor sees waiting bar, not buttons Retain manual exploratory pass for UX polish. | Presentation exposes legalActionsForHero only for current actor. ActionBarView renders fold/check/call based on LegalActions. Core revalidates and rejects illegal actions. | Passed: build-ios-apps test_sim fold action flow after unifying fold/check/call/raise controls to 8pt rounded action buttons; betting/invalid-action tests passed in package suite. | Pass |  |  | Pass
HM-017 | Raise slider and presets | Retain exploratory chip/value pass; automated Poker iPhone 16 flow now adjusts the raise slider to min, max, and mid positions, taps +1 BB, pot, 1/2 pot, closes, reopens, and submits | Raise panel clamps selected total to legal min/max. Header shows the selected raise total with close affordance, the slider gets a full-width row, presets include +1 BB, 1/2 pot, pot, and the explicit Raise button submits .raise(to:) then closes. | Passed: raise panel simplified into header/full-width slider/preset-submit rows and presets now share the 8pt action-control shape; Swift package suite 306/306 and build-ios-apps test_sim adjusts the slider to min, max, and mid positions, verifies accessible selected values, taps +1 BB, pot, 1/2 pot, close, reopen, and submit through the full RiverInteractionTests suite on Poker iPhone 16. | Pass |  |  | Pass
HM-018 | Waiting state | Observe other players' turns and timeout-resolved states; verify named actor waiting copy in multi-participant iMessage Retain manual exploratory pass for UX polish. | When no legal hero actions are available and hand is not resolved, PokerTableActionArea renders WaitingBar with presentation.waitingText and table.waiting identifier. Non-actors see the current player's saved name in the waiting copy when available; folded players still get a next-hand message. | Passed: package frontend contract tests for non-actor waiting mode, named current-player waiting copy, folded-player waiting copy, table.waiting identifier, and 8pt waiting bar shape. | Pass |  |  | Pass
HM-019 | Turn clock and timeout | Wait past timeout on simulator, reopen/act, verify deterministic timeout action Retain manual exploratory pass for UX polish. | GameState stores turnStartedAt/turnDuration. TurnClock/GameTimeout resolve stale turns lazily when a client loads or acts. Active hero/opponent seat accessibility labels include the normalized turn-clock duration so the timer is not purely visual. | Passed: package timeout tests plus frontend contract tests proving render-time timeout resolution, normalized visual clocks, and active seat accessibility labels that include the shared turn-clock duration; full RiverInteractionTests passed on Poker iPhone 16. | Pass |  |  | Pass
HM-020 | Leave active table confirmation | Retain extended manual multi-player pass to verify excluded players stay out of later hands | PokerTableView overlays LeaveTableButton when not game-over. The leave entry point is a visible 44pt icon control, exposes confirmation state for accessibility, reveals cancel/confirm actions, and confirm sends leaveGame. Core marks player left/forfeits hand as appropriate. | Passed: visible 44pt leave control with confirmation-state accessibility and unified 8pt framed stay/leave confirmation controls; Swift package suite 306/306 and build-ios-apps leave cancel plus destructive confirm heads-up game-over paths passed on Poker iPhone 16. | Pass |  |  | Pass
HM-021 | Street advancement | Retain iMessage bubble-summary manual pass; standalone Poker iPhone 16 now verifies flop, turn, river, showdown result, and Deal next hand | StreetAdvancement advances only after betting round completion. Board cards are dealt by stage, pot/display summaries update. The standalone UI test now checks board counts at flop, turn, and river, then verifies the showdown/result state and Deal next hand action. | Passed: package street advancement/full hand tests plus build-ios-apps check/call board-progression UI path on Poker iPhone 16 covering flop, turn, river, showdown result, and Deal next hand. | Pass |  |  | Pass
HM-022 | Uncontested hand result | Fold all but one player and verify chip movement/result/deal-next Retain manual exploratory pass for UX polish. | UncontestedAward and hand lifecycle assign pot, mark hand complete, and presentation shows a single accessible winner/result banner separate from any Deal next command. | Passed: build-ios-apps test_sim fold-to-result/deal-next flow after splitting winner status from Deal next command and fixing duplicate table.result accessibility; hand result tests passed. | Pass |  |  | Pass
HM-023 | Showdown and side pots | Retain manual all-in/split-pot UX pass; package tests cover side-pot math and frontend contract now covers accessible revealed cards/winners | HandEvaluator, ShowdownRanking, SidePotAwarding, and HandSettlement compute ranked winners and payments. UI highlights winning cards and winner text, reveals contesting players' showdown cards, and the seat accessibility summary identifies revealed cards plus winning seats. | Passed: package showdown/side-pot/best-of-seven tests plus frontend contract for accessible revealed showdown cards and winning seats; still needs manual all-in UX pass. | Pass |  |  | Pass
HM-024 | Deal next hand | Retain multi-hand manual pass for dealer/stacks; standalone Poker iPhone 16 verifies Deal next hand, fresh hole cards, cleared board, and hidden deal-next action | When hand complete and onDealNext exists, action area shows result status and a short Deal next hand command with a stable action identifier. Operation uses new seed, rotates dealer, excludes left/broke players, handles game over, and returns the UI to a fresh hand with an empty board. | Passed: build-ios-apps test_sim deal-next flow with short Deal next hand label, fresh hole cards, cleared board, and hidden deal-next action on Poker iPhone 16; next-hand package tests passed. | Pass |  |  | Pass
HM-025 | Game over presentation | Play/eliminate to one winner or construct fixture; verify no leave/action controls and final live table says wins game Retain manual exploratory pass for UX polish. | If state.isGameOver, renderer shows GameOverView. The finished-game prompt exposes one deterministic accessible element labelled with Game over plus the final summary and announces that no actions are available. In the live table, the result banner distinguishes a final game win from a hand win with 'wins game'. Core rejects further game actions as gameOver. | Passed: package frontend contract tests for game-over renderer ordering, deterministic Game over accessibility label/value, and live table final-result copy that says wins game; game-over lifecycle tests passed; full RiverInteractionTests passed on Poker iPhone 16. | Pass |  |  | Pass
HM-026 | Stable compact text | Run full build/test and manually inspect every button in iPhone 16 simulator Retain manual exploratory pass for UX polish. | StableText is used on key buttons to constrain one-line text, scale where appropriate, and avoid clunky wrapping in action surfaces. | Passed: package frontend contract tests after stable-text helper test update, compact open-table affordance polish, tighter first-run profile layout, unified 8pt lobby/conversation/table/leave controls, centralized control radius, and centralized table action/compact control heights in Theme.Metrics; full RiverInteractionTests suite passed on Poker iPhone 16. | Pass |  |  | Pass
HM-027 | Automation identifiers | Write/expand UI tests to hit every ID in this workbook Retain manual exploratory pass for UX polish. | HoldemAccessibility centralizes IDs for profile, lobby, conversation, table actions, raise panel, leave confirmation, and waiting/result states. | Passed: build-ios-apps test_sim used key accessibility IDs; frontend contract tests passed, including selected avatar trait, profile preview label, table.board, table.leave accessibility value, conversation.gameOver label/value, and active seat clock labels. | Pass |  |  | Pass
HM-028 | Payload durability and legacy handling | Run package tests after every payload-affecting UI/transport change Retain manual exploratory pass for UX polish. | Payload coders encode table messages/operations through URL-safe payloads. Legacy tests cover prior formats and malformed cases. | Passed: package payload serialization/durability/legacy tests. | Pass |  |  | Pass
HM-029 | Duplicate/stale operation protection | Replay same operation payload and older revision in tests/manual harness Retain manual exploratory pass for UX polish. | Operation IDs are normalized/history-capped. Applied operation IDs and TableRevisionTracker reject duplicate/stale/wrong-base operations. | Passed: package operation history/revision tests. | Pass |  |  | Pass
HM-030 | Standalone pass-and-play demo | Reinstall on Poker iPhone 16, play many hands, document UX/logistics issues Retain manual exploratory pass for UX polish. | River starts GameTableScreen in dark mode. GameController uses local lobby state and pass-and-play current actor as hero. | Passed: build-ios-apps test_sim standalone pass-and-play smoke path on Poker iPhone 16, including saved-profile identity appearing in the acting hero seat and leave-confirmation game-over copy saying wins game. | Pass |  |  | Pass

## Errors
Error ID | Story ID | Area | Observed behavior | Expected behavior | Severity | Source/Screen | Fix status | Retest status | Notes